## SettingGoals
(DAT) QC Circle_Setting Goals
11th QC circle (Dec~May)
No. | Team | SelectedTopic (Name of the Effort) | Content Detail | Reason for this topic | Determination methods (How to proceed) | Current Value | Goal Value | Expected Goal Completion Date (mmddyyyy) | Comment | Schedule & Progress Dec (※Must Fill Out this field) | Schedule & Progress Jan (※Must Fill Out this field) | Schedule & Progress Feb (※Must Fill Out this field) | Schedule & Progress Mar (※Must Fill Out this field) | Schedule & Progress Apr (※Must Fill Out this field) | Issues/Problems (※Optional) | Comment
| SONAR-FR | DAT Learning system web application | When analysis our team most frequently projects, There are generally (1). Finding related files ( jsp,bean and factory files) for screen investigation (2). Finding proper account for integration test from oracle database These two tasks mostly drain time and effort of our team member. For reduction of manually tracking files for screen investigation and manually writing query and search, required account on database this tool is used to do these tasks. The main function of the tool is (1). User enter <<aid>> of form and automatically search for related files ( jsp,bean and factory files) . (2). User select account types, company, server etc. and will automatically generate the required account from database. | - To improve the quality and productivity of major team projects. - To reduce time spend on manual screen and login account investigation for testing. - To reduce reliance on external applications and documentation. - To improve team's efficiency. | Testing Support Tool 1. Create schedule to develop and learn necessary technologies for tool development. 2. Investigate and implement requirement definition and optimal architectural patterns for tool development. 3. Coding development implementation. 4. Tool testing, feedback collection from team member and performance optimization. | 0 | 0.10 (人月) | 2026-05-10 | 06/06/2025 [SD&QC Team] Please keep going as the plan. | Accomplished steps - Create schedule for specific tasks assignment. Ongoing steps - Investigate require skills and Java language (Especialy Java Swing UI) - Identify the features, methods and requirements for tool development. Current Value - 0.20 人月 Goal Value - 0.10 人月 | Finished steps - Investigate require skills and Java (Change from Swing UI to Java FX) - Identify the features, methods and requirements - Basic and UI Design (70%) Ongoing steps - Basic and UI Design - Tool Development current Current Value - 0.20 人月 Goal Value - 0.10 人月 | Finished steps - Basic and UI Design - 100% - Tool Development >> AID tool features - 100% >> Custom query features - 100% >> Overall coding development - 80% Ongoing steps - Pre defined query tool features coding development - Unit test specification/Evidence creation and execution. Current Value - 0.20 人月 Goal Value - 0.10 人月 | Finished steps - Tool Development >> Pre defined Query features - 100% >> Extract AID data from web features - 100% >> Overall coding development - 100% - Tool manual creation - 100% - Unit test specification/Evidence creation and execution - 60% Ongoing steps - Unit test specification/Evidence creation and execution - Tool Optimization (UI,Performance, Code Refactor) Current Value - 0.10 人月 Goal Value - 0.10 人月 | Finished steps - Unit test specification/Evidence creation and execution - 100% - Tool Optimization >> DB Connection Optimization - 100% >> Search Function Optimization- 100% Ongoing steps - Bug Fix - Power Point Creation Current Value - 0.10 人月 Goal Value - 0.10 人月 -------------------------- Result Value - 0.10 人月 Meet with Goal Value